## Internet
| Agency Implementation Activities |  | Economic Devel. |  | Judicial AOC |  | Attorney General |  | Unified Prosec. |  | Personnel |  | Human Rights |  | Higher Ed Assist. |  | Judicial Retirement |  | LRC; Gen. Assbly |  | Sec. Of State |  | Military Affairs, etc. |  | Local Govt. |  | Post-Sec. Educ. |  | KY Retirement |  | Auditor |  | Election Finance |  | B/C Team |  | CFC |  | Agric. |  | Labor |  | KOSH Comm. |  | Workers Comp |  | Revenue |  | Workforce Development |  | Fair Board |  | CHS |  | Just.-OS |  | Jus.-Train |  | Jus.-Juv. |  | Educ. |  | KTRS |  | Arts/Hum |  | PPR |  | Natural Resources |  | State Police |  | Corrections |  | Fish and Wildlife |  | Horse Park |  | Tourism OS |  | Travel Devel. |  | Parks |  | Finance |  | County Services |  | DOT |  | Treasury |  | DIS
| AIL |  | Jerry Frantz |  | Laura Stammel |  | Cindy James |  | Kim Furnish |  | Walt Gaffield |  | Alfred & Anna Adams |  | Londa Wolanin |  | Donna Stockton-Early |  | Phelps & Barton |  | Rebecca Feland |  | Hubert Payton |  | Jim Reynolds |  | Pat Sawyer |  | Joe Hutchison |  | Stephanie Robey |  | Mac Bushart |  | Randy Smith |  | Terry Thompson |  | Charlene Galyon |  | Kevin Cardwell |  | Sue Ramsey |  | Barbara Pulliam |  | TBD |  | J. Friel, G. Brunker, R. Jump |  | Greg Randall |  | Bailey, Carr |  | David Garr |  | Ken Schwendeman |  | Mike Mullins |  | Glen Bradt |  | James Chadwell |  | Doris Jones |  | Nick Piacsek |  | Boyce Wells |  | Mike Hulett |  | Gerry Howard |  | Bob Bates |  | Mike Scales |  | Hugh Smith, Joan White |  | Hugh Smith |  | Hugh Smith, Louis Tandy |  | Ellen Nolan |  | Marie Bramblett |  | Taylor Manley |  | Eugene Harrell |  | Ruth Ann Sparks
| ALM |  | D. Knowles |  | D. Knowles |  | D. Knowles |  | D. Knowles |  | D. Knowles |  | D. Knowles |  | D. Knowles |  | D. Knowles |  | D. Knowles |  | D. Knowles |  | D. Knowles |  | D. Knowles |  | D. Knowles |  | D. Knowles |  | D. Knowles |  | D. Knowles |  | D. Knowles |  | R. Keltner |  | R. Gilligan |  | D. Knowles |  | D. Knowles |  | D. Knowles |  | R. Peter |  | R. Peter |  | R. Peter |  | D. Hall |  | D. Hall |  | D. Hall |  | D. Hall |  | R. Gilligan |  | B. Wilkinson |  | R. Gilligan |  | R. Gilligan |  | S. Beam |  | S. Beam |  | S. Beam |  | V. Grover |  | V. Grover |  | V. Grover |  | V. Grover |  | V. Grover |  | G. Schwartztrauber |  | G. Schwartztrauber |  | G. Schwartztrauber |  | Schwartztrauber |  | R. Peter
| Status | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 4 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 4 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 3 | 2 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | % | 1 | (% Agencies @ Level) | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 | %
6.5.4 | Gather STARS Agency COA Codes | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.5.8 | Define Agency COA/Budget Control Usage | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.5.25 | Develop Agency Implementation Plans | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 0 |  | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 0 |  | 1 | X | 1 | X | 1 | X | 95.65%
6.6.1 | Organize Interface Development | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 100%
6.6.2 | Design Agency System Changes | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | X |  | X | 0 |  | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 97.78%
6.6.3 | Modify the MARS Coding Structure (for each interface) | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 0 |  | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | NA | 0 |  | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | NA | 0 |  | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | X |  | X | 0 |  | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 0 |  | 1 | X | 1 | X | 88.89%
6.6.4 | Program New Interfaces (for each interface) | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 0 |  | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | NA | 0 |  | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | NA | 0 |  | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | X |  | X | 0 |  | 0 |  | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 0 |  | 1 | X | 1 | X | 86.67%
6.6.5 | System Test Interfaces with Modified Agency/Legacy Systems | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 0 |  | 1 | NA | 1 | NA | 1 | NA | 0 |  | 1 | NA | 1 | NA | 0 |  | 1 | NA | 0 |  | 1 | NA | 1 | NA | 1 | NA | 0 |  | 1 | NA | 0 |  | 1 | NA | 1 | NA | 1 | X |  | X | 0 |  | 0 |  | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 0 |  | 1 | NA | 1 | X | 80%
6.7.1.1 | Validate Statewide COA Crosswalk | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.7.1.2 | Validate Capital Projects Accounts Crosswalk | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | X | 100%
6.7.1.3 | Validate Grants Crosswalk | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | X | 100%
6.8.1.1.1 | Identify Procurement Data Forms to Populate - Org. | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X |  | X |  | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 100%
6.8.1.3.1 | Identify Financial Data Forms to Populate - COA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.8.1.3.2 | Identify Financial Data Forms to Populate - Project Billing/Grants | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | NA | 100%
6.8.1.3.3 | Identify Financial Data Forms to Populate - Inventory | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 0 |  | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | NA | 97.83%
6.8.1.3.4 | Identify Financial Data Forms to Populate - Cost Allocation | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | X | X | X | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | X | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | X | 100%
6.8.1.3.5 | Identify Financial Data Forms to Populate - Fixed Assets | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | X | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | X | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | X | X | X | X | X | X | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | X | 100%
6.8.3.1 | Populate Purchasing Forms (Mandatory) | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 0 |  | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 97.83%
6.8.4.3 | Populate COA Forms | 1 | NA | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 100%
6.9.1.1 | Attend Training Meeting | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.9.1.2 | Identify & Register Training Participants | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.11.1 | Evaluate Existing Hardware and Software | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 100%
6.11.2 | Determine Software & Hardware Needs | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 100%
6.11.3 | Acquire Appropriate Hardware & Software | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 0 |  | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 0 |  | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 95.65%
6.11.4 | Generate Current Agency Network Diagram | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 0 |  | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 97.83%
6.11.5 | Complete MARS Network & User Questionnaire | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 100%
6.11.6 | Determine Network Needs | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 0 |  | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 97.83%
6.14.1 | Assign Security Lead & Schedule Meetings | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.14.2 | Attend MARS Security Training Session | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.14.3 | Compile List of MARS Users | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.14.4 | Determine Security Needs on 7/1/99 | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X |  | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.14.5.1 | Determine Multi-Agency Accesses | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | X | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.14.5.2 | Determine MARS System Access Requirements | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | X | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X |  | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.14.6.1 | Select Purchasing Profile | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | X | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.14.6.2 | Select Budgeting Profile | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | X | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.14.6.3 | Select Financial Profile | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | X | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.14.6.4 | Select Reporting Profile | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | X | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.14.7 | Determine Current User System Access | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | X | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.14.8 | Complete MARS Security Profile Request Form | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | X | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.14.9 | Obtain Appropriate Approvals for Security Ids | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | X | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.14.10 | Return Request Form to Central Security Team via ALM | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | X | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | X | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X |  | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 100%
6.16.1 | Compile list of MARS Workflow Users | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 100%
6.16.2 | Assign User Approval Authority Types | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 100%
6.16.3 | Review Statewide Cited Authorities | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 100%
6.16.4 | Review List of Procurement Desktop Document Types | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | X | 100%
6.16.5 | Select Document Approval Paths | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 0 |  | 1 | NA | 0 |  | 1 | X | 1 | X | 95.65%
6.16.6 | Identify Commodity and Funding Exceptions | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X |  | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | X | 1 | X | 1 | NA | 100%
7.2.1 | As-Is Activity Analysis | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | X | 0 |  | 0 |  | 1 | X | 1 | X | 1 | X | 0 |  | 1 | X | 1 | X | 0 |  | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | X | 1 | NA | 1 | NA | 1 | X | 1 | X | 1 | NA | 1 | X | 0 |  | 1 | X | 89.13%
| Status % |  | 100% |  | 100% |  | 100% |  | 100% |  | 93.62% |  | 100% |  | 100% |  | 95.74% |  | 94.59% |  | 100% |  | 100% |  | 93.62% |  | 97.3% |  | 95.74% |  | 100% |  | 97.87% |  | 100% |  | 89.36% |  | 100% |  | 97.73% |  | 97.14% |  | 100% |  | 97.87% |  | 100% |  | 91.49% |  | 95.74% |  | 100% |  | 100% |  | 100% |  | 100% |  | 97.87% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 97.87% |  | 97.87% |  | 91.49% |  | 97.87% |  | 100% | 98.31%
Legend:
X = Complete; NA = Not Applicable
Shaded blocks = In Progress; Empty = Not Started
Status (% Complete Critical Tasks Past Due)
1 = 91% to 100%
2 = <=90%
3 = <=70%
4 = <=50%