## Sheet1
Required Task
Optional Task
Task # | Task Name | Start Date | Finish Date
6.5 | Agency System Usage Analysis | 1998-11-13 08:00 | 1999-02-15 17:00
6.5.1 | Agency Goals & Objectives | 1998-11-25 08:00 | 1998-11-30 17:00
6.5.2 | Complete Planning Questionnaire | 1998-11-23 08:00 | 1998-11-30 17:00
6.5.3 | Refine Assignments/Schedule Meetings | 1998-11-26 08:00 | 1998-11-30 17:00
6.5.4 | Gather STARS Agency COA Codes | 1998-11-16 08:00 | 1998-11-30 17:00
6.5.5 | Review Current Processes | 1998-11-13 08:00 | 1998-12-10 17:00
6.5.6 | Review Usage Analysis Technique | 1998-12-01 08:00 | 1999-01-31
6.5.7 | Review MARS COA/Budget Control Model | 1998-11-24 08:00 | 1998-11-25 17:00
6.5.8 | Define Agency COA/Budget Control Usage | 1998-11-25 08:00 | 1999-02-01
6.5.9 | Define Purchasing/Payables Usage | 1998-12-01 08:00 | 1999-02-10
6.5.10 | Define Revenue/Receivables Usage | 1998-12-01 08:00 | 1999-02-10
6.5.11 | Define Internal Orders & Billing Usage | 1998-12-01 08:00 | 1999-02-10
6.5.12 | Define Project Billing & Job Costing Usage | 1998-12-01 08:00 | 1999-02-10
6.5.13 | Define Grants & Cost Allocation Usage | 1998-12-01 08:00 | 1999-02-10
6.5.14 | Define Fixed Asset Usage | 1998-12-01 08:00 | 1999-02-10
6.5.15 | Define Inventory Usage | 1998-12-01 08:00 | 1999-02-10
6.5.16 | Define Budget Preparation Usage | 1998-12-01 08:00 | 1999-02-10
6.5.17 | Define Disbursements Usage | 1998-12-01 08:00 | 1999-02-15
6.5.18 | Define Travel usage | 1998-12-01 08:00 | Post 7/1/99
6.5.19 | Consolidate Agency-Specific Policy & Procedures Requirements | 1999-01-01 08:00 | 1999-02-15 17:00
6.5.20 | Consolidate Agency-Specific Interface Requirements | 1999-01-01 08:00 | 1999-02-15 17:00
6.5.21 | Consolidate Agency-Specific Conversion Requirements | 1999-01-01 08:00 | 1999-02-15
6.5.22 | Consolidate Agency-Specific Reporting Requirements | 1999-01-01 08:00 | 1999-02-15 17:00
6.5.23 | Consolidate Agency-Specific Security Requirements | 1999-01-01 08:00 | 1999-02-15 17:00
6.5.24 | Consolidate Agency-Specific Training Requirements | 1999-01-01 08:00 | 1999-02-15 17:00
6.5.25 | Develop Agency Implementation Plans | 1999-01-01 08:00 | 1999-02-15 17:00
6.5.26 | Issue Identification & Resolution | 1998-11-24 08:00 | 1999-02-15
6.6 | Agency Interfaces Implementation Tasks | 1998-11-10 08:00 | 1999-02-26
6.6.1 | Organize Interface Development | 1998-11-10 08:00 | 1998-11-23 17:00
6.6.2 | Design Agency System Changes | 1998-12-03 | 1999-01-29
6.6.3 | Modify the Agency/Legacy System to Use MARS | 1999-02-01 | 1999-02-19
6.6.4 | Program & Unit Test Interface Software | 1999-02-01 | 1999-02-19
6.6.5 | System Test Interfaces with the Modified Agency/Legacy System | 1999-02-22 | 1999-02-26
6.7 | Data Conversion Tasks | 1999-01-08 | 1999-06-17
6.7.1 | Validate Accounting Crosswalks | 1999-01-08 | 1999-03-15
6.7.1.1 | Validate Statewide COA Crosswalk | 1999-01-08 | 1999-02-15
6.7.1.2 | Validate Capital Projects Accounts Crosswalk | 1999-02-01 | 1999-03-01
6.7.1.3 | Validate Grants Crosswalk | 1999-02-04 | 1999-03-15
6.7.2 | Determine Agency-Specific Data Conversion Requirements | 1999-01-08 | 1999-02-01
6.7.3 | Design Data Extract Programs/Manual Procedures | 1999-03-01 | 1999-03-15
6.7.4 | Develop and Test Data Extract Programs/Manual Procedures | 1999-03-15 | 1999-04-01
6.7.5 | Extract Data to be Loaded into MARS | 1999-04-30 | 1999-06-17
6.7.5.1 | Extract Data to be Loaded into MARS -- Simulations | 1999-04-30 | 1999-05-10
6.7.5.2 | Extract Data to be Loaded into MARS -- Production | 1999-05-10 | 1999-06-17
6.8 | Data Prep, Setup & Loading | 1999-02-05 | 1999-06-01
6.8.1 | Identify Data Forms to Populate | 1999-02-05 | 1999-02-15
6.8.1.1 | Identify Procurement Data Forms to Populate | 1999-02-05 | 1999-02-15
| Organization Data | 1999-02-05 | 1999-02-15
| Agency-Specific Template Data | 1999-02-05 | 1999-02-15
| Fixed Assets Exceptions Data | 1999-04-13 | Ongoing
| Procurement Card Data | 1999-03-26 | 1999-03-29
6.8.1.2 | Identify Budget Data Forms to Populate | 1999-03-26 | 1999-04-15
6.8.1.3 | Identify Financial Data Forms to Populate | 1999-02-05 | 1999-02-15
| Chart of Accounts | 1999-02-05 | 1999-02-15
| Inventory | 1999-02-05 | 1999-02-15
| Project Billing/Grants | 1999-02-05 | 1999-02-15
| Cost Allocation (return form) | 1999-02-05 | 1999-02-15
6.8.2 | Determine Population Method | 1999-02-15 | 1999-03-01
6.8.3 & 4 | Perform Manual & Automated Population | 1999-03-16 | 1999-05-10
| Populate Mandatory Procurement Form F6.8.1.1a (Central Team) | 1999-02-05 | 1999-03-15
| Populate Optional Procurement Forms | 1999-06-21 | Ongoing
| Populate Budgeting Forms | 1999-03-29 | 1999-06-01
| Populate COA Forms | 1999-02-15 | 1999-03-15
| Populate Project Billing/Grants Forms | 1999-03-15 | 1999-04-15
| Populate Inventory Forms | 1999-03-15 | 1999-07-01
| Populate Fixed Assets Exceptions | 1999-07-01 | Ongoing
6.9 | MARS Training Tasks | 1999-02-05 | 1999-06-30
6.9.1 | Perform Mandatory MARS Training Tasks | 1999-02-05 | 1999-06-15
6.9.1.1 | Attend Training Meetings | 1999-02-05 | 1999-03-10
6.9.1.2 | Identify & Register Training Participants | 1999-03-10 | 1999-03-22
6.9.1.3 | Coordinate Attendance at Training Sessions | 1999-04-01 | 1999-08-30
6.9.2 | Perform Optional MARS Agency-Specific Training Tasks | 1999-03-01 | 1999-06-30
6.9.2.1 | Identify Target Audience | 1999-03-01 | 1999-05-15
6.9.2.2 | Review MARS Training Materials | 1999-03-15 08:00 | 1999-05-31
6.9.2.3 | Determine Training Constraints | 1999-04-01 | 1999-05-31
6.9.2.4 | Develop Outlines for Agency Custom Training | 1999-04-01 | 1999-05-31
6.9.2.5 | Develop Preliminary Training Schedule | 1999-04-15 | 1999-05-31
6.9.2.6 | Develop Agency Specific Training Materials | 1999-04-01 | 1999-05-31
6.9.2.7 | Develop Detailed Agency Training Schedule | 1999-04-01 08:00 | 1999-05-31
6.9.2.8 | Establish/Secure Training Facility & Environment (Custom Only) | 1999-04-01 08:00 | 1999-05-31
6.9.2.9 | Review/Revise Training Schedule & Materials& Deliver Training | 1999-05-15 | 1999-06-30
6.10 | MARS Policies & Procedures Tasks | 1998-11-10 08:00 | 1999-04-15
6.10.1 | Form Agency P/P Teams and Schedule Meetings | 1998-11-25 08:00 | 1999-02-22
6.10.2 | Document Current Processes | 1998-11-17 08:00 | 1999-02-15
6.10.3 | Review Current MARS-Related Policies | 1998-12-15 08:00 | 1999-01-13
6.10.4 | Review New MARS Related Policies | 1999-02-22 | 1999-04-28
6.10.5 | Identify & Document Policy Issues & Forward for Review | 1999-02-22 | 1999-04-28
6.10.6 | Review current Procedures | 1998-11-10 08:00 | 1999-01-13
6.10.7 | Review MARS Procedures | 1999-02-22 | 1999-05-31
6.10.8 | Identify Procedures for Agency Customization | 1999-02-22 | 1999-06-01
6.10.9 | Create Customized Procedures & Submit for Approval | 2009-02-22 | 1999-06-15
6.11 | Hardware, Software, & Network Readiness Tasks | 1998-11-10 08:00 | 1999-04-30 17:00
6.11.1 | Evaluate Existing Hardware and Software | 1998-11-10 08:00 | 1998-11-23 17:00
6.11.2 | Determine Software & Hardware Needs | 1998-11-24 08:00 | 1998-12-21 17:00
6.11.3 | Acquire Appropriate Hardware & Software | 1999-01-12 08:00 | 1999-04-30 17:00
6.11.4 | Generate Current Agency Network Diagram | 1998-11-10 08:00 | 1998-11-23 17:00
6.11.5 | Complete MARS Network & User Questionnaire | 1998-11-13 08:00 | 1998-12-07 17:00
6.11.6 | Determine Network Needs | 1998-12-07 08:00 | 1999-02-15
6.12 | MARS Reports Tasks | No tasks due | No tasks due
6.13 | Agency-Specific Enhancement Logging Tasks | No tasks due | No tasks due
6.14 | MARS Security Tasks | 1999-03-26 | 1999-04-30
6.14.1 | Assign Security Lead & Schedule Meetings | 1999-03-26 | 1999-03-31
6.14.2 | Attend MARS Security Training Session | 1999-04-01 | 1999-04-05
6.14.3 | Compile List of MARS Users | 1999-03-26 | 1999-04-05
6.14.4 | Determine Security Needs on 7/1/99 | 1999-03-29 | 1999-04-09
6.14.5 | Determine MARS Security Requirements | 1999-03-29 | 1999-04-09
6.14.5.1 | Determine Multi-Agency Accesses | 1999-03-29 | 1999-04-09
6.14.5.2 | Determine MARS System Access Requirements | 1999-03-29 | 1999-04-09
6.14.6 | Assign User to MARS Profile | 1999-04-09 | 1999-04-15
6.14.6.1 | Select Purchasing Profile | 1999-04-09 | 1999-04-15
6.14.6.2 | Select Budgeting Profile | 1999-04-09 | 1999-04-15
6.14.6.3 | Select Financial Profile | 1999-04-09 | 1999-04-15
6.14.6.4 | Select Reporting Profile | 1999-04-09 | 1999-04-15
6.14.7 | Determine Current User System Access | 1999-04-16 | 1999-04-20
6.14.8 | Complete MARS Security Profile Request Form | 1999-04-21 | 1999-04-23
6.14.9 | Obtain Appropriate Approvals for Security Ids | 1999-04-23 | 1999-04-29
6.14.10 | Return Request Form to Central Security Team via ALM | 1999-04-29 | 1999-04-30
6.15 | MARS Acceptance Testing Tasks | No tasks due | No tasks due
6.16 | MARS Workflow Tasks
6.16.1 | Compile list of MARS Workflow Users | 1999-04-26 | 1999-04-30
6.16.2 | Assign User Approval Authority Types | 1999-04-28 | 1999-05-04
6.16.3 | Review Statewide Cited Authorities | 1999-04-26 | 1999-04-30
6.16.4 | Review List of Procurement Desktop Document Types | 1999-04-26 | 1999-04-30
6.16.5 | Select Document Approval Paths | 1999-05-03 | 1999-05-14
6.16.6 | Identify Commodity and Funding Exceptions | 1999-05-10 | 1999-05-14
6.17 | MARS Travel Tasks | No tasks due | No tasks due
6.18 | MARS Post-Implementation Support Tasks (Release 4) | 1999-07-01 08:00 | No tasks due
6.19 | MARS Cutover Tasks (future AIN updates)
7 | Change Leadership
7.1 | Plan Stakeholder Identification, Analysis and Communications | 1998-10-08 | *
7.1.1 | Identify and Analyze Agency Stakeholders | 1998-10-08 | *
7.1.2 | Conduct a Communications Audit | 1998-10-08 | *
7.1.3 | Create an Administrative Services Communications Plan | 1998-10-08 | *
7.2 | Perform As-Is Activity Analysis | 1998-08-28 | 1998-10-14
7.3 | Perform Workforce Transition Planning | 1999-03-19 | 1999-04-14
7.4 | Perform Leadership Awareness Activities | Ongoing | Ongoing
*Does not need to be submitted to Central Team.